## GANTT Chart
DATA VIS APP PROJECT
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17
[6 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Extension 1
| Wireframe/Outline Planning/Design | 2020-11-25 | 2020-11-27 | 3 | 100% | bar: WEEK 1 M to WEEK 1 T
| ETL (Extract, Transform, Load) Data | 2020-11-27 | 2020-11-29 | 2 | 100% | bar: WEEK 1 T to WEEK 1 Th
| Code Draft Extension | 2020-11-29 | 2020-12-05 | 7 | 90% | bar: WEEK 1 Th to WEEK 2 F
| Code Organization and Modularity | 2020-12-05 | 2020-12-07 | 2 | 80% | bar: WEEK 2 M to WEEK 3 T
| Quality Check/Debugging | 2020-12-07 | 2020-12-14 | 7 | 70% | bar: WEEK 3 T to WEEK 4 W
| Finishing Touches/Embellishment | 2020-12-14 | 2020-12-29 | 15 | 70% | bar: WEEK 4 W to WEEK 7 T
| Finalize Extension | 2020-12-29 | 2020-01-15 | 15 | 70% | bar: WEEK 7 T to WEEK 10 M
| Document Extension and Report Building | 2020-01-15 | 2020-01-30 | 13 | 20% | bar: WEEK 10 M to WEEK 12 W
| Publish Extension for Final Project | 2018-01-20 | 2020-01-22 | 2 | 10% | bar: WEEK 12 Th to WEEK 12 F
Extension 2
| Wireframe/Outline Planning/Design | 2020-11-25 | 2020-11-27 | 3 | 100% | bar: WEEK 1 M to WEEK 1 T
| ETL (Extract, Transform, Load) Data | 2020-11-27 | 2020-11-29 | 2 | 100% | bar: WEEK 1 T to WEEK 1 Th
| Code Draft Extension | 2020-11-29 | 2020-12-05 | 7 | 90% | bar: WEEK 1 Th to WEEK 2 F
| Code Organization and Modularity | 2020-12-05 | 2020-12-07 | 2 | 80% | bar: WEEK 2 M to WEEK 3 T
| Quality Check/Debugging | 2020-12-07 | 2020-12-14 | 7 | 70% | bar: WEEK 3 T to WEEK 4 W
| Finishing Touches/Embellishment | 2020-12-14 | 2020-12-29 | 15 | 70% | bar: WEEK 4 W to WEEK 7 T
| Finalize Extension | 2020-12-29 | 2020-01-15 | 15 | 70% | bar: WEEK 7 T to WEEK 10 M
| Document Extension and Report Building | 2020-01-15 | 2020-01-30 | 13 | 20% | bar: WEEK 10 M to WEEK 12 W
| Publish Extension for Final Project | 2018-01-20 | 2018-01-23 | 2 | 10% | bar: WEEK 12 Th to WEEK 12 F
Extension 3
| Wireframe/Outline Planning/Design | 2020-01-02 | 2020-01-05 | 3 | 100% | bar: WEEK 8 M to WEEK 8 W
| ETL (Extract, Transform, Load) Data | 2020-01-05 | 2020-01-08 | 3 | 100% | bar: WEEK 8 W to WEEK 8 F
| Code Draft Extension | 2020-01-07 | 2020-01-15 | 7 | 60% | bar: WEEK 8 Th to WEEK 9 F
| Code Organization and Modularity | 2020-01-15 | 2020-01-23 | 7 | 60% | bar: WEEK 9 F to WEEK 11 M
| Quality Check/Debugging | 2020-01-23 | 2020-02-01 | 7 | 40% | bar: WEEK 11 M to WEEK 12 T
| Finishing Touches/Embellishment | 2020-02-01 | 2020-02-15 | 15 | 20% | bar: WEEK 12 T to WEEK 15 M
| Finalize Extension | 2020-02-15 | 30/2 | 15 | 20% | bar: WEEK 15 M to WEEK 17 F
| Document Extension and Report Building | 2020-02-25 | 30/2 | 5 | 10% | bar: WEEK 17 M to WEEK 17 F
| Publish Extension for Grading | 30/2 | 2020-03-01 | 2 | 10% | bar: WEEK 17 Th to WEEK 17 F
Final Project
| Document Full Project | 2020-02-25 | 30/2 | 5 | 50% | bar: WEEK 17 M to WEEK 17 F
| Reflection on Project | 2020-02-25 | 30/2 | 5 | 50% | bar: WEEK 17 M to WEEK 17 F
| Evaluation | 2020-02-25 | 30/2 | 5 | 30% | bar: WEEK 17 M to WEEK 17 F
| Publish Final Project for Grading | 2020-02-25 | 30/2 | 5 | 10% | bar: WEEK 17 M to WEEK 17 F
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])